ACTIVITY 3 WORKSHEET

Build the Product Backlog and Run Sprint 1 Planning

Agile Project Management for Business  ·  TGS-2023018967  ·  Topic 2  ·  LO2  ·  60 minutes

| TEAM MEMBERS ____________________________________ | DATE ____________________________________ |
| --- | --- |
| TOOL https://alfredang.github.io/scrum/ | ACTIVITY FOLDER activities/activity-03-*/ |

THE SITUATION HarbourFront's committee has approved a restart: 6 sprints of 2 weeks, one team of 7 people, and a hard demonstration to the top 5 customers in 12 weeks. Nothing from the old 96-page document is carried over unexamined. You are the team, with your trainer as Product Owner. Sprint 1 planning starts now.

Record your team's output below.

1.  Sprint 1 SPRINT GOAL (one business outcome, not a list)

2.  Story 1 — text, points, Given/When/Then

3.  Story 2 — text, points, Given/When/Then

4.  Story 3 — text, points, Given/When/Then

5.  Total stories in the product backlog (target 12+)

6.  MoSCoW split — count of Must / Should / Could / Won't

7.  Stories pulled into Sprint 1, and total points (target ~20)

8.  Any story you SPLIT, and how you split it

9.  Your team's DEFINITION OF DONE (checklist)

10.  Confirm: does every Sprint 1 story serve the sprint goal? Which did you remove?

SELF-CHECK BEFORE YOU FINISH

☐   Sprint 1 holds about 20 points, every story in it serves the one written sprint goal, no story exceeds 8 points, every story has Given/When/Then acceptance criteria, and the Definition of Done is visible to the whole team. A sprint whose stories serve four unrelated goals is a task list, not a sprint.

☐   Every team member can explain the output, not just the person who typed it.

☐   The artefact is exported or screenshotted into this worksheet.

© 2026 Tertiary Infotech Academy Pte Ltd  ·  UEN: 201200696W  ·  Full step-by-step instructions: Learner Guide, Activity 3