Tertiary Infotech Academy Pte Ltd

UEN: 201200696W

LESSON PLAN

For

Agile Project Management for Business

TGS Ref No: TGS-2023018967

Conducted by

Tertiary Infotech Academy Pte Ltd

UEN: 201200696W

Version v9.0

DOCUMENT VERSION CONTROL RECORD

| Version Number | Effective Date of Release | Summary of Included Changes | Author |
| --- | --- | --- | --- |
| v9.0 | 17 August 2026 | Full content revamp. Rebuilt on a single-source content module. Expanded Agile theory (Manifesto values/principles, Scrum accountabilities/artefacts/events, Lean, Kanban + Little's Law, XP, DSDM, scaling). Added the five Agile metrics with worked interpretation. Replaced generic exercises with 8 tool-based activities on one running case study (HarbourFront Logistics). Added activity debriefs and full TSC mapping. | Dr Alfred Ang |
| v8.0 | 28 November 2022 | Previous released version. | Tertiary Infotech Academy |

TABLE OF CONTENTS

1.  Course Information	4

1.1  Target Audience	4

1.2  Entry Requirements	4

1.3  Learning Outcomes	4

1.4  TSC Mapping — Abilities and Knowledge Assessed	4

2.  Training Resources	5

2.1  Trainer Resources	5

2.2  Learner Resources	6

2.3  Online Tools Used in the Activities	6

3.  Daily Training Schedule	6

3.1  Day 1 — The Agile mindset and the essentials	6

3.2  Day 2 — Building and running an Agile team	8

3.3  Assessment Session (Day 2, after instructional hours)	11

4.  Activity Summary	11

5.  Assessment Plan	13

6.  Trainer Delivery Notes	14

6.1  Timing Discipline	14

6.2  Facilitating the Activities	14

6.3  Common Learner Misconceptions to Correct	14

6.4  Contingency	14

# 1.  Course Information

| Field | Detail |
| --- | --- |
| Course Title | Agile Project Management for Business |
| WSQ Course Code | TGS-2023018967 |
| Training Provider | Tertiary Infotech Academy Pte Ltd (UEN: 201200696W) |
| Course Duration | 2 days · 16 instructional hours (8 hours per day) · plus 2 hours assessment |
| Delivery Mode | Physical classroom, synchronous Zoom, or corporate on-site delivery |
| Class Size | Maximum 20 learners per class |
| TSC Reference | Business Agility · ICT-BIN-4038-1.1 |
| Assessment | Written Assessment (WA — SAQ, 1 hour) and Case Study (CS, 1 hour). Both open book. |
| Trainer | Dr Alfred Ang |
| Version | v9.0 · 17 August 2026 |
| Course Page | https://www.tertiarycourses.com.sg/wsq-agile-project-management-for-business.html |

## 1.1  Target Audience

This course is designed for professionals who lead, coordinate or contribute to projects and who need to deliver in conditions where requirements change. Suitable job roles include:

Project Manager

Scrum Master

Product Owner

Business Analyst

Team Leader

IT Project Manager

Change Manager

Operations Manager

Programme Manager

## 1.2  Entry Requirements

Basic computer operation proficiency

Minimum 3 GCE 'O' Level passes including English, or Workplace Literacy (WPL) Level 5

Minimum 1 year of working experience

A positive learning attitude and willingness to participate in team activities

## 1.3  Learning Outcomes

By the end of this course, learners will be able to:

LO1: Adopt a new Agile mindset for project management

LO2: Share and implement Agile practices within the teams

LO3: Build an Agile team to execute and track the project performance

## 1.4  TSC Mapping — Abilities and Knowledge Assessed

All content maps to the Skills Framework TSC “Business Agility” (ICT-BIN-4038-1.1). Nothing is assessed that is not taught and practised.

| Code | TSC Ability | Taught in |
| --- | --- | --- |
| A1 | Share information actively within and across teams to bridge operational barriers | Topic 2 · Activity 4 |
| A2 | Organise work in alignment with operational priorities | Topics 1–2 · Activities 2, 4 |
| A3 | Implement Agile or lean practices to reduce waste and defects in operating procedures and practices | Topics 2–3 · Activities 3, 7 |
| A4 | Measure progress against targets for defined business outcomes on a regular basis | Topic 3 · Activities 5, 7, 8 |
| A5 | Experiment with new ideas, products or services | Topic 1 · Activity 1 |
| A6 | Assess work performance and quality to ensure continuous improvement | Topic 3 · Activities 6, 7, 8 |
| A7 | Manage individual work responsibilities and take ownership of individual and team outcomes | Topic 3 · Activities 5, 6, 8 |

| Code | TSC Knowledge | Taught in |
| --- | --- | --- |
| K1 | Methods to analyse current and future business operating landscapes | Topic 1 · Activity 2 |
| K2 | Methods to analyse current and future customer needs and preferences | Topic 1 · Activity 1 |
| K3 | Organisational policies, processes and standards | Topic 1 · Activity 2 |
| K4 | Types of change management methodologies, tools and practices | Topic 2 |
| K5 | Types of team composition and formation models | Topic 3 · Activities 4, 5 |
| K6 | Values and principles of Agile methodologies | Topic 2 · Activity 3 |
| K7 | Types of Agile methodologies and practices | Topic 2 · Activity 3 |

# 2.  Training Resources

## 2.1  Trainer Resources

Master Trainer Slides (PPTX and PDF), 120 slides, version v9.0

This Lesson Plan

Learner Guide with full step-by-step activity instructions

Assessment instruments: WA (SAQ) question paper and answer key; Case Study question paper and marking guide (trainer-only — never distributed to learners)

Laptop, projector and internet access

Whiteboard and markers

Sticky notes and A3 flip-chart paper for the team activities

Planning-poker cards (Fibonacci: 1, 2, 3, 5, 8, 13, 21) — one deck per team

## 2.2  Learner Resources

Learner Slides (PDF)

Learner Guide (PDF) — contains every activity step

A laptop or tablet with a modern web browser and internet access

The HarbourFront Logistics case brief (in the Learner Guide)

## 2.3  Online Tools Used in the Activities

All tools are browser-based. Nothing needs to be installed and no login is required.

| Tool | URL | Used in |
| --- | --- | --- |
| 5 Whys | https://alfredang.github.io/5whys/ | Root-cause analysis in the sprint retrospective (Activity 6) |
| Fishbone | https://alfredang.github.io/fishbone/ | Cause-and-effect analysis of delivery problems (Activity 2) |
| Pareto Chart | https://alfredang.github.io/paretochart/ | Prioritising the 20% of causes driving 80% of defects (Activity 7) |
| RACI Matrix | https://alfredang.github.io/raci/ | Clarifying Agile role accountability (Activity 4) |
| Scrum Board | https://alfredang.github.io/scrum/ | Running the sprint board, backlog and burndown (Activities 3, 5, 8) |
| Design Thinking | https://alfredang.github.io/designthinking/ | Empathising with customers to shape the product vision (Activity 1) |

# 3.  Daily Training Schedule

Each training day runs 09:30–18:30 and delivers exactly 8 instructional hours. The 1-hour lunch break is excluded from instructional time; short tea breaks are counted within it. Slide references are to the Master Trainer Slides version v9.0.

## 3.1  Day 1 — The Agile mindset and the essentials

Instructional hours: 8.00 (excludes the 1-hour lunch break).

| Time | Hrs | Topic / Activity | Content and Delivery Notes | Method | Slides |
| --- | --- | --- | --- | --- | --- |
| 09:30 – 09:45 | 0.25 | Digital Attendance (AM) & Welcome | Trainer displays the SSG digital attendance QR code; learners scan and submit. Housekeeping and safety brief. | Trainer-led Admin | 2–7 |
| 09:45 – 10:15 | 0.50 | Trainer & Learner Introductions · Ground Rules | Trainer introduction. Learners share role, industry and their biggest project frustration — captured on the whiteboard and referred back to all day. | Discussion Ice-breaker | 4–6 |
| 10:15 – 10:45 | 0.50 | Learning Outcomes · TSC Mapping · Course Outline | The three learning outcomes, how the TSC abilities and knowledge map to each topic, the six tools, and the running HarbourFront case study. | Trainer-led Q&A | 8–16 |
| 10:45 – 11:00 | 0.25 | Assessment Briefing & Funding Criteria | Assessment format (WA + Case Study), open-book scope, the assessment flow, 75% attendance and TRAQOM requirements. | Trainer-led | 17–19 |
| 11:00 – 12:15 | 1.25 | Topic 1: Introduction to Agile Project Management (Part 1) | Are we building the right thing? The traditional project lifecycle and the challenges every PM recognises. The waterfall model, its assumptions, and why it struggles. The cost-of-change curve. (K1, K3) | Trainer-led Diagrams Discussion | 20–26 |
| 12:15 – 13:00 | 0.75 | Activity 1: Empathise with the Customer (start) | Teams of 3–4 use the Design Thinking tool to build an empathy map and persona for Priya Menon, then reframe the requirement as a customer-value problem statement. (K2, A5) | Hands-on Team activity Design Thinking tool | 37–39 |
| 13:00 – 14:00 | — | LUNCH BREAK (1 hour — not counted as instructional time) | Digital Attendance (PM) taken on return. | Break | 44 |
| 14:00 – 14:30 | 0.50 | Activity 1 debrief · Digital Attendance (PM) | Each team presents its reframed problem statement in 90 seconds. Trainer draws out the difference between signed-off scope and delivered value. | Presentation Debrief | 39 |
| 14:30 – 15:45 | 1.25 | Topic 1: Introduction to Agile Project Management (Part 2) | What Agile actually is. Agile vs traditional. Inverting the iron triangle. Methods to analyse the operating landscape (PESTLE, SWOT, Five Forces, scenario planning) and customer needs (personas, journey maps, JTBD, Kano, A/B). Agile beyond software. When Agile is NOT the right answer. (K1, K2, A2, A5) | Trainer-led Comparison tables Case examples | 27–36 |
| 15:45 – 16:30 | 0.75 | Activity 2: Diagnose the Waterfall Failure (Fishbone) | Teams use the Fishbone tool to analyse why CustomerConnect failed, tag each cause structural or behavioural, and pair each structural cause with an Agile practice. (K1, K3, A2) | Hands-on Team activity Fishbone tool | 40–42 |
| 16:30 – 16:45 | 0.25 | Activity 2 debrief · Topic 1 recap | Why most causes tag as structural, and the two causes Agile does not fix on its own. | Debrief | 42–43 |
| 16:45 – 18:15 | 1.50 | Topic 2: Agile Essentials (Part 1) | The Agile Manifesto: 4 values read correctly and the 12 principles. The Scrum framework end to end — 3 accountabilities, 3 artefacts and their commitments, 5 events. The Definition of Done. (K6, K7) | Trainer-led Framework diagram Discussion | 45–56 |
| 18:15 – 18:30 | 0.25 | Day 1 recap and Q&A | Consolidate the mindset shift and preview Day 2. | Q&A | 73–74 |

## 3.2  Day 2 — Building and running an Agile team

Instructional hours: 8.00 (excludes the 1-hour lunch break).

| Time | Hrs | Topic / Activity | Content and Delivery Notes | Method | Slides |
| --- | --- | --- | --- | --- | --- |
| 09:30 – 09:45 | 0.25 | Digital Attendance (AM) & Day 1 recap | Learners scan the SSG QR code. Quick recall of the four values and the three Scrum accountabilities. | Admin Q&A | 74 |
| 09:45 – 11:00 | 1.25 | Topic 2: Agile Essentials (Part 2) | Lean and the seven principles, the eight wastes. Kanban's five practices and Little's Law. Extreme Programming. Choosing between Scrum, Kanban and Scrumban. DSDM/AgilePM and the scaling frameworks. (K7, A3) | Trainer-led Comparison table Board walkthrough | 57–63 |
| 11:00 – 11:45 | 0.75 | Topic 2: Change Management and Resistance (K4) | Finding Agile support: naming and answering each stakeholder's actual fear. Making the adoption stick — willing pilot, visible wins, evolutionary change, coach then withdraw. The honest warning about 'more for less'. (K4, A1) | Trainer-led Role discussion | 64–65 |
| 11:45 – 12:45 | 1.00 | Activity 3: Build the Product Backlog & Run Sprint 1 Planning | Teams write user stories with Given/When/Then criteria, test them against INVEST, estimate with planning poker, order with MoSCoW, write one sprint goal and load Sprint 1 to 20 points. Trainer acts as Product Owner. (K6, K7, A3) | Hands-on Team activity Scrum Board tool Planning poker | 66–69 |
| 12:45 – 13:00 | 0.25 | Activity 3 debrief | Why the sprint goal is the artefact that makes a sprint reviewable, and why splitting by workflow step beats splitting by technical layer. | Debrief | 69 |
| 13:00 – 14:00 | — | LUNCH BREAK (1 hour — not counted as instructional time) | Digital Attendance (PM) taken on return. | Break | — |
| 14:00 – 14:45 | 0.75 | Activity 4: Clarify Role Accountability (RACI) · Attendance (PM) | Teams map 12 project decisions against 5 roles, audit for duplicate/missing Accountables, and resolve the conflicting-priorities escalation. (K5, A1, A2) | Hands-on Team activity RACI tool | 70–72 |
| 14:45 – 15:30 | 0.75 | Topic 3: Building the Agile Team and Setting the Vision | Team composition and formation models, generalising specialists, Tuckman's stages and adaptive leadership, servant leadership, and setting a shared vision. (K5) | Trainer-led Diagrams | 75–80 |
| 15:30 – 16:15 | 0.75 | Topic 3: User Stories, Prioritisation and Estimation | Story anatomy, the three Cs, INVEST and the split rule. Prioritisation techniques. Relative estimation, story points, planning poker and the 13-point rule. Timeboxing and Parkinson's Law. (A2, A7) | Trainer-led Worked examples | 81–85 |
| 16:15 – 17:15 | 1.00 | Activity 5: Execute Sprint 1 and Track It on the Board | Teams simulate all 10 sprint days with daily stand-ups, a WIP limit of 3, and three trainer-injected impediments. They plot the burndown and compute actual velocity. (K5, A4, A7) | Hands-on Simulation Scrum Board tool | 99–101 |
| 17:15 – 17:45 | 0.50 | Topic 3: The Five Agile Metrics, Waste and Risk | Sprint burndown, release burndown, velocity, control chart and cumulative flow diagram — what each shows, how to read it, and the anti-patterns. Little's Law worked numerically. Root-cause tools, the Pareto principle, value stream mapping, risk as anti-value, and technical debt and ownership. (A3, A4, A6, A7) | Trainer-led Chart interpretation | 86–98 |
| 17:45 – 18:15 | 0.50 | Activities 6, 7 & 8: Retrospective, Pareto and Forecast | Activity 6: full retrospective with 5 Whys to a changeable root cause and one SMART action. Activity 7: Pareto of 120 defects to find the vital few. Activity 8: velocity forecast as a range, and reading the CFD/control chart to name the bottleneck. (A3, A4, A6, A7) | Hands-on Team activities 5 Whys · Pareto · Scrum Board | 102–110 |
| 18:15 – 18:30 | 0.25 | Topic 3 recap · Course summary and next steps | Consolidate the three learning outcomes, the eight key takeaways, and the recommended follow-on courses. Final Q&A before the feedback survey. | Recap Q&A | 111–115 |

## 3.3  Assessment Session (Day 2, after instructional hours)

The 2-hour assessment sits outside the 16 instructional hours.

| Time | Hrs | Session | Notes | Method | Slides |
| --- | --- | --- | --- | --- | --- |
| 18:30 – 18:45 | — | Course Feedback and TRAQOM Survey (mandatory) | Learners complete the TRAQOM survey on lms-tms.tertiaryinfotech.com. | Admin | 118 |
| 18:45 – 19:00 | — | Digital Attendance (Assessment) and Assessment Briefing | Assessment attendance submitted. Rules restated: open book (slides, Learner Guide, approved materials only), no discussion, no photography. | Admin | 116–117 |
| 19:00 – 20:00 | — | Written Assessment (WA) — Short-Answer Questions | Individual, open book, 1 hour. | Assessment | 116 |
| 20:00 – 21:00 | — | Case Study (CS) | Individual, open book, 1 hour. An applied business scenario with structured tasks. | Assessment | 116 |
| 21:00 – 21:15 | — | Results, feedback and appeal process | Competent / Not Yet Competent communicated, with the appeal route explained. | Admin | 117 |

# 4.  Activity Summary

Every activity advances the same running case — HarbourFront Logistics Pte Ltd and its CustomerConnect portal — so the artefacts learners build compound across the two days. Full step-by-step instructions for each activity are in the Learner Guide.

| # | Activity | Tool | Min | LO | TSC | Learner Output |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Empathise with the Customer to Reframe a Failing Project | Design Thinking | 45 | LO1 | K2, A5 | A completed empathy map and persona for Priya Menon, a reframed problem statement, and a ranked list of the top 3 customer-value features with the reasoning for each. |
| 2 | Diagnose the Waterfall Failure with a Fishbone Analysis | Fishbone | 45 | LO1 | K1, K3, A2 | A completed fishbone diagram with 6 categories and at least 18 causes, each tagged as structural or behavioural, plus a one-page recommendation identifying which causes Agile addresses and which it does not. |
| 3 | Build the Product Backlog and Run Sprint 1 Planning | Scrum Board | 60 | LO2 | K6, K7, A3 | A product backlog of at least 12 estimated user stories in priority order, a Sprint 1 backlog of about 20 points, one written sprint goal, and a Definition of Done agreed by the whole team. |
| 4 | Clarify Agile Role Accountability with a RACI Matrix | RACI Matrix | 45 | LO2 | K5, A1, A2 | A completed RACI matrix covering 12 activities across 5 roles, a list of the anti-patterns found, and the corrected matrix with the specific change that resolves the developers' escalation. |
| 5 | Execute Sprint 1 and Track It on the Scrum Board | Scrum Board | 60 | LO3 | K5, A4, A7 | A completed 10-day sprint board, a burndown chart with all 10 data points, an impediment log with the resolution of each of the 3 injections, and the actual velocity achieved. |
| 6 | Run the Sprint Retrospective with 5 Whys Root-Cause Analysis | 5 Whys | 45 | LO3 | A6, A7 | A completed 5 Whys chain of at least 5 levels reaching an actionable root cause, plus one SMART improvement action with a named owner, a measure, and a place in the Sprint 2 backlog. |
| 7 | Prioritise Defect Causes with a Pareto Chart | Pareto Chart | 45 | LO3 | A3, A4, A6 | A completed Pareto chart of 8 defect categories with a cumulative line, the identified vital few, and a Sprint 4 improvement commitment with a numeric target and the projected defect reduction. |
| 8 | Forecast the Release from Velocity and Read the Agile Metrics | Scrum Board | 45 | LO3 | A4, A6, A7 | A velocity-based forecast range in sprints and calendar dates, a release burndown, a written interpretation of the CFD and control chart naming the bottleneck, and a one-paragraph answer to the committee. |

# 5.  Assessment Plan

| Instrument | Detail |
| --- | --- |
| Written Assessment (WA) | Written Assessment (WA) — Short-Answer Questions (SAQ), 1 hour, open book. Assesses the underpinning knowledge (K1–K7): the business landscape, customer analysis methods, Agile values and principles, Agile methodologies, change management and team formation models. |
| Case Study (CS) | Case Study (CS) — an applied business scenario with structured tasks, 1 hour, open book. Assesses applied ability (A1–A7): reading a business scenario, ordering a backlog, interpreting metrics, diagnosing a root cause and recommending action. |
| Conditions | Open book: slides, Learner Guide and approved course materials only. Individual work. No discussion, no photography, no recording. |
| Competency Decision | Learners must be assessed Competent in BOTH instruments. A learner assessed Not Yet Competent in either instrument may be re-assessed. |
| Attendance | A minimum of 75% attendance is required to be eligible for assessment and funding. Learners must be assessed Competent in both instruments. |
| Appeal | A learner may appeal an assessment decision in writing within 7 working days. The appeal is reviewed by a second qualified assessor. |

# 6.  Trainer Delivery Notes

## 6.1  Timing Discipline

The activities are the course. If you are running late, compress the concept slides — never the activities. Learners are assessed on applied ability.

Announce a hard time for each activity and hold it. Activity 5 (the 10-day sprint simulation) will overrun if you do not call each simulated day yourself.

Keep the debrief for each activity — it is where the learning is consolidated and where the TSC link is made explicit.

## 6.2  Facilitating the Activities

Form teams of 3–4 on Day 1 and keep them for both days, so their case artefacts accumulate.

In Activity 3, you play the Product Owner. Push back on teams that accept every story; make them defend the ordering.

In Activity 5, inject the three impediments on cue (Day 3 stale feed, Day 5 capacity loss, Day 7 mid-sprint request). The Day 7 request is the real test — watch whether teams protect the sprint or simply absorb the work.

In Activity 6, do not let a team stop at 'the carrier's fault'. Keep asking why until the cause is something the team itself can change.

In Activity 8, expect teams to recommend 'increase velocity'. That is the teachable moment — walk them back to the control chart and Little's Law.

## 6.3  Common Learner Misconceptions to Correct

| Misconception | The correction |
| --- | --- |
| “Agile means no planning.” | Agile plans continuously and at multiple levels. It replaces one large upfront plan with frequent replanning. |
| “Agile means no documentation.” | Agile documents 'barely sufficiently' — just in time and for a stated reason. The discipline moves; it does not disappear. |
| “Velocity measures productivity.” | Velocity is a forecasting input. Rewarding it produces estimate inflation and destroys the forecast. |
| “Agile gets more done for less money.” | Agile buys responsiveness, earlier value and lower risk of building the wrong thing — not free capacity. |
| “The Scrum Master runs the team.” | The Scrum Master owns the process and removes impediments. The Developers own how the work is done. |
| “Working faster reduces cycle time.” | Little's Law: cycle time falls when WIP falls. Starting less finishes more. |
| “Agile suits every project.” | Fixed regulatory scope, no customer access or physical irreversibility all weigh against it. Say so honestly. |

## 6.4  Contingency

If a tool URL is unreachable, run the activity on flip-chart paper — every tool here has a paper equivalent, and the thinking is what is assessed.

If the class is smaller than 6, run two teams and have them cross-review each other's artefacts instead of presenting to the room.

If a learner arrives without a laptop, pair them into a team that has one; every activity is a team activity.